## Gantt Chart
Task ID | Task Name | Assigned Member ID | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Status
1 | Project Planning & Requirement Study | All Team | 1 Week | Completed | [9 empty] | Completed
2 | System Architecture Design | 2677517 | 1 Week | Completed | [9 empty] | Completed
3 | Database Design (MySQL) | 2677527 | 1 Week |  | Completed | [8 empty] | Completed
4 | Frontend UI Design | 2677527 | 2 Weeks |  | Completed | Completed | [7 empty] | Completed
5 | Landing Page Development | 2677529 | 1 Week |  |  | Completed | [6 empty] | Completed | Completed
6 | Product Management Module | 2677527 | 2 Weeks |  |  | Completed | Completed | [5 empty] | Completed | Completed
7 | Category Management Module | 2677527 | 1 Week |  |  |  | Completed | [5 empty] | Completed | Completed
8 | Order Management Module | 2677527 | 2 Weeks |  |  |  | Completed | Completed |  |  |  |  | Completed | Completed
9 | Flask Backend API Development | 2677527 | 2 Weeks |  |  |  | Completed | Completed |  |  |  |  | Completed | Completed
10 | Database Integration | 2677527 | 1 Week |  |  |  |  | Completed |  |  |  |  | Completed | Completed
11 | Frontend & Backend Integration | 2677527 | 1 Week | [5 empty] | Completed |  |  |  | Completed | Completed
12 | Testing & Bug Fixing | All Team | 2 Weeks | [5 empty] | Completed | Completed |  |  | Completed | Completed
13 | Documentation & Diagrams | 2677530 | 2 Weeks | [6 empty] | Completed | Completed |  | Completed | Completed
14 | Mockup & UI Improvements | 2677527 | 1 Week | [7 empty] | Completed |  | Completed | Completed
15 | Presentation Slides Preparation | 2677527 | 1 Week | [8 empty] | Completed | Completed | Completed
16 | Final Review & Rehearsal | All Team | 1 Week | [9 empty] | Completed | Completed
17 | Final Submission | All Team | 1 Day | [9 empty] | Completed | Completed